## project
wp | activity | start_date | end_date
Inception | Deciding things | 1 | 6
Preparation | Questionnaire development | 3 | 6
Preparation | Translation | 4 | 7
Preparation | CAPI Scripting | 5 | 10
Training | Interviewer Training | 6 | 12
Fieldwork | Interviewing | 9 | 12
Fieldwork | Monitoring | 3 | 5
Post-Fieldwork | Data Editing | 8 | 9
Post-Fieldwork | Documentation | 6 | 9

## spots
activity | spot_type | spot_date
1.1. That admin activity | D | 5
1.3. Fancy admin activity | E | 7
2.2. Actual R&D stuff | O | 7
2.2. Actual R&D stuff | O | 9